## Project Plan
Milestone | Work Package | Objective | Activities |  | Deliverables | Format of Deliverable | Timeframe |  |  | Year 1 Budget incl. VAT |  |  |  | TOTAL
|  |  | No. | Details |  |  | Start (Month) | End (Month) | Duration | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
1. Initiation | 1.1. Project Legal & Administration | To ensure project management and legal & administration requirements are in place for the successful implementation of the project | 1.1.1 | Understand project objectives, scope, and deliverables. | Completed project proposal | PDF | Month 1 | Month 1 | 1 Month | 0 | 0 | 0 | 0 | 0
|  |  | 1.1.2 | Ensure all project related contracts are in place for the project | Signed Contracts
Sub-Total 1 | [9 empty] | 0 | 0 | 0 | 0 | 0
2. Planning | 2.1 Project Planning | Establish a clear, legally binding framework for the project, ensuring collaboration and understanding between all parties. | 2.2.1 | Develop Project Execution Plan in consultation with TIA Specialits | Project Execution Document | PDF | Month 1 | Month 1 | 1 Month | 0 | 0 | 0 | 0 | 0
|  |  | 2.2.2 | Host Project kick off meeting to ensure all relevant stakholders understand how the project will be implemented
| 2.2. Business Sustainability Model | To build a business sustainability model that aims to reduce dependence on government support for the technology in the future. | 2.2.3 | Develop a stakholder map to identifiy funding sources and potential partners for Umhlatuze | Stakeholder map including funding sources |  | Month 1 | Month 2 | 12 Months | 0 | 20000 | 20000 | 10000 | 50000
|  |  | 2.2.4 | Develop a business sustainability model for Sisanda App Universe | Business sustainability model |  | Month 3 | Month 9
|  |  | 2.2.5 | Source funding proposals to support the sustainability of Sisanda App Universe beyond the duration of this project at Umhlathuze | 3 Funding Proposals |  | Month 9 | Month 12
Sub-Total 2 | [9 empty] | 0 | 20000 | 20000 | 10000 | 50000
3. Execution (Deployment) | 3.1. Deployment Readiness | To prepare for deployment of the Sisanda App at all selcted schools | 3.1.1 | Identify and finalize product sites | Finalized list of sites signed off by City of uMhlathuze | PDF | Month 2 | Month 2 | 1 Week | 0 |  | 0 | 0 | 0
|  |  | 3.1.2 | Address any potential gaps that might impact project implementation. | Updated Risk Register | Excel Sheet | Month 2 | Month 2 | 2 Week | 0 |  | 0 | 0 | 0
|  |  | 3.1.3 | Procure and deliver of 165 tablets to the selected schools | Invoice and Delivery Notes. | PDF | Month 2 | Month 2 | 1 Week | 506664 |  |  |  | 506664
|  |  | 3.1.4 | Purchase school Licences | Proof of payment of licenses | .xsl | Month 2 | Month 2 | 1 Week | 402336 |  | 0 | 0 | 402336
|  |  | 3.1.5 | Install the app on tablets for all participating schools. | Successful installation test report for all devices | .apk | Month 2 | Month 2 | 1 Week | 0 |  | 0 | 0 | 0
|  |  | 3.1.6 | Conduct quality assurance checks to ensure optimal app performance of the app on all devices | Quality Assurance Report | PDF | Month 2 | Month 2 | 1 Week
| 3..2 Training | To Equip teachers and IT staff with the skills to use the app effectively. | 3.2..1 | Schdeule training sessions for teachers and IT staff. | Scanned Attendance Register and Training Report | PDF | Month 3 | Month 3 | 1 Month | 5000 | 0 | 0 | 0 | 5000
|  |  | 3.2..2 | Conduct hands-on demonstration sessions. | Scanned Attendance Register and Training Report | Website Page
|  |  | 3.2..3 | Update and distribute user manuals and FAQs. | Proof of updated manuals and distribution lsists | Printed Manuals
| 3.3 Deployment | To successfully roll out the app across the selected designated schools. | 3.3.1 | Distribute tablets to the schools. | Signed delivery notes | PDF | Month 3 | Month 12 | 8 Month | 5000 | 0 | 0 | 0 | 5000
|  |  | 3.3.2 | Provide delivery notes for teachers or school management to sign, confirming delivery.
|  |  | 3.3.3 | Provide on-site support during the initial days of implementation.
Sub-Total 3 | [9 empty] | 919000 | 0 | 0 | 0 | 919000
4. Support, Monitoring and Evaluation | 4.1.Monitoring and Support | To ensure smooth app operation and address any arising issues. | 4.1.1 | Establish a helpline or support portal for schools to report issues or seek assistance. | Support portal | Online Portal | Month 3 | Month 12 | 9 Month | 5000 | 0 | 6000 | 0 | 11000
|  |  | 4.1.2 | Monitor app usage, performance, and gather user feedback. | Monthly monitoring reports | PDF
|  |  | 4.1.3 | Provide any and all required updates to the Sisanda App. | Update Reports | APK
| 4.2. Feedback Collection | To assess user experience and identify areas for improvement. | 4.2.1 | Conduct surveys or focus group discussions with teachers and students. | Feedback reports from users | PDF | Month 3 | Month 12 | 9 Month | 0 | 0 | 0 | 0 | 0
|  |  | 4.2.2 | Analyze feedback to discern trends, challenges, or suggestions. | Feedback reports from users | PDF
|  |  | 4.2.3 | Plan enhancements based on the feedback received. | Update Product roadmap | Trello
| 4.3.Continuous Improvement | To ensure the app's continued relevance and efficacy. | 4.3.1 | Release updates or patches based on feedback and technological advancements. | Updated app versions | APK | Month 3 | Month 12 | 9 Month | 0 | 5000 | 5000 | 5000 | 15000
|  |  | 4.3.2 | Schedule refresher training sessions on any new features added to the app | Training sessions for new features | PDF and Support page
|  |  | 4.3.3 | Engage with schools for sustained collaboration and improvement. | Feedback reports | PDF
Sub-Total 4 | [9 empty] | 5000 | 5000 | 11000 | 5000 | 26000
5. Closure | 5.1.Project Review and Reporting | Conclude the implementation phase and transition to regular operations. | 5.1.1 | Document the implementation process, challenges encountered, and lessons learned. | Final project close out eport | PDF | Month 10 | Month 12 | 2 Month | 0 | 0 | 0 | 5000 | 5000
Sub-Total 5 | [9 empty] | 0 | 0 | 0 | 5000 | 5000
Grand Total (Sub-Total 1 +2+3+4+5) | [9 empty] | 924000 | 25000 | 31000 | 20000 | 1000000
Disbursement Schedule
| Disbursement 1 (30%) | 300000
| Disbursement 2 (50%) | 500000
| Disbursement 3 (20%) | 200000
1000000

## Breakdown expediture
Sisanda.com
| INVOICES | [5 empty] | LABOUR | OPERATIONAL COST: |  | CAPITAL EQUIPMENT
nr | Date | Name of Company | Description | Invoice | Link for invoice | Link for POP | Personnel | Overheads/Admin/ Bank Charge | Office material and Rent | Procure and deliver of 165 tablets to the selected schools | Purchase school Licences
1 | 23-Feb-2024 | PURCH BARGAIN BOOKS NORTHR4854422142204564 7454 | Banks charges | 55 |  | As Per Bank Statement |  |  | 55
2 | 23-Feb-2024 | FNB App Transfer To Mbuso Cele | Learning and Training | 21000 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing | 21000
3 | 23-Feb-2024 | POS Purchase 109.99 Canva* I0406 | Subscription for the standard used | 109 |  | As Per Bank Statement |  |  | 109
4 | 23-Feb-2024 | POS Purchase 109.99 Google *Yout | Subscription for the standard used | 109 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 109
7 | 24-Feb-2024 | PURCH 500 FETWAY INVESTME4854422142204564 7429 | Digital Assets | 185 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 185
8 | 24-Feb-2024 | 234 City Properties | Rent | 528.31 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 528.31
10 | 24-Feb-2024 | FNB App Prepaid Airtime 27631707952 | Airtime | 55 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 55
13 | 26-Feb-2024 | POS Purchase Payfast African Tech | VR Headset | 15499 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 15499
14 | 26-Feb-2024 | POS Purchase 59.99 Apple.Com/Bil | Subcription for the storage | 59.99 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 59.99
15 | 27-Feb-2024 | POS Purchase 52.99 Google Storag | Subcription for the storage | 52.99 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 52.99
16 | 27-Feb-2024 | Fuel Purchase Tshela Filling Stat | Petrol | 933.59 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 933.59
17 | 28-Feb-2024 | Internet Pmt To 23107Arcatamabaso | Rent Deposit | 3835 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 3835
18 | 28-Feb-2024 | POS Purchase PNP Crp Botshabelo | Office Breakfast | 59.98 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  | 59.98
19 | 28-Feb-2024 | POS Purchase Yoco *Design N Pr | Flash drive and Printing | 113 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 113
20 | 28-Feb-2024 | POS Purchase 194.64 Facebk *Vcrx | Facebook Paid AD | 194.64 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 194.64
21 | 28-Feb-2024 | Fuel Purchase Shell Botshabelo | Petrol | 150 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 150
23 | 29-Feb-2024 | Send Money App Dr Send | Tutor / User Tester | 2150 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  |  | 2150
24 | 29-Feb-2024 | POS Purchase Istore Loch Logan | Hardware and testing devices | 21098 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  |  | 21098
25 | 01-Mar-2024 | Internal Debit Order FNB Insure 2631760 F64241 | FNB Insurance for business | 630 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 630
26 | 01-Mar-2024 | Magtape Debit Iclix 265727214 Netcash | Subscription for the standard use(Internet) | 450 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 450
27 | 01-Mar-2024 | POS Purchase PNA Northridge Mall | Text Books for content creation | 290.6 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  |  | 290.6
28 | 01-Mar-2024 | POS Purchase Bargain Books North | Text Books for content creation | 611 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  |  | 611
29 | 01-Mar-2024 | POS Purchase 18.53 Cloud Vhj4Xp | Subcription for the storage | 365.36 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 365.36
30 | 01-Mar-2024 | Bank Charges Feb | February Bank Charges | 523.76 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  | 523.76
31 | 04-Mar-2024 | FNB App Prepaid Airtime | Airtime | 9 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 9
32 | 04-Mar-2024 | Internet Pmt To Sgs-Neo-Makaye | Tutor / User Tester | 1000 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  |  | 1000
33 | 04-Mar-2024 | POS Purchase Afrihost Com 3 | Subscription for the standard use(Internet) | 219 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 219
34 | 04-Mar-2024 | POS Purchase 5.00 Fetway Investm | Digital assets for project | 98.91 |  | As Per Bank Statement |  |  |  |  | 98.91
35 | 04-Mar-2024 | POS Purchase 10.03 Google*Cloud | Subcription for the storage | 197.82 |  | As Per Bank Statement |  |  | 197.82
36 | 05-Mar-2024 | Electricity Prepaid Electricity | Prepaid Electricity | 70 |  | As Per Bank Statement |  |  | 70
37 | 05-Mar-2024 | Electricity Prepaid Electricity | Prepaid Electricity | 200 |  | As Per Bank Statement |  |  | 200
38 | 05-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
40 | 05-Mar-2024 | Internet Pmt To Sgs-Lungile | Tutor / User Tester | 1200 |  | As Per Bank Statement |  |  |  |  | 1200
41 | 05-Mar-2024 | POS Purchase Engen Mangaung 1 St | Food | 93.7 |  | As Per Bank Statement |  |  |  | 93.7
43 | 05-Mar-2024 | POS Purchase Wimpy JHB Int Airp | Food | 200 |  | As Per Bank Statement |  |  |  | 200
44 | 06-Mar-2024 | POS Purchase 59.99 Apple.Com/Bil | Subcription for the storage | 59.99 |  | As Per Bank Statement |  |  | 59.99
45 | 07-Mar-2024 | Fuel Purchase Shell Botshabelo | Petrol | 150 |  | As Per Bank Statement |  |  |  | 150
46 | 08-Mar-2024 | FNB App Prepaid Airtime | Aitime | 55 |  | As Per Bank Statement |  |  | 55
47 | 08-Mar-2024 | Send Money App Dr | Tutor / User Tester | 750 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  |  | 750
48 | 08-Mar-2024 | FNB App Prepaid Airtime | Airtime | 9 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 9
49 | 08-Mar-2024 | Electricity Prepaid Electricity | Electricity | 500 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  | 500
50 | 08-Mar-2024 | POS Purchase S2S*Moiponesupermak | Food | 26 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 26
54 | 09-Mar-2024 | POS Purchase Sasol Technikon | Food | 51.9 |  | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing |  |  |  | 51.9
55 | 09-Mar-2024 | POS Purchase Mcd Bloemfontein | Food | 72.9 |  | As Per Bank Statement |  |  |  | 72.9
56 | 11-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
57 | 11-Mar-2024 | Card Replacement | New Bank Card | 130 |  | As Per Bank Statement |  | 130
58 | 11-Mar-2024 | POS Purchase S2S*Willowssupermar | Food | 24 |  | As Per Bank Statement |  |  |  |  | 24
59 | 11-Mar-2024 | POS Purchase Shell Gysie Pienaar | Food | 51.9 |  | As Per Bank Statement |  |  |  |  | 51.9
60 | 11-Mar-2024 | POS Purchase Stadium Mandela Vie | Food | 104.8 |  | As Per Bank Statement |  |  |  |  | 104.8
61 | 11-Mar-2024 | POS Purchase Game Bloemfontein | Office equipment | 499 |  | As Per Bank Statement |  |  | 499
62 | 11-Mar-2024 | POS Purchase Gbc Petroleum Pty L | Petrol | 700 |  | As Per Bank Statement |  |  |  | 700
63 | 11-Mar-2024 | Fuel Purchase Mandela View Motors | Petrol | 1020.95 |  | As Per Bank Statement |  |  |  | 1020.95
64 | 11-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
66 | 12-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
67 | 12-Mar-2024 | POS Purchase Engen Mangaung 1 St | Food | 24.9 |  | As Per Bank Statement |  |  | 24.9
68 | 12-Mar-2024 | POS Purchase Yoco *Arcata Squa | Food | 54 |  | As Per Bank Statement |  |  | 54
71 | 12-Mar-2024 | POS Purchase Makro Bloemfontein | Office equipment | 1999 |  | As Per Bank Statement |  |  | 1999
73 | 12-Mar-2024 | Fuel Purchase Tshela Filling Stat | Petrol | 150 |  | As Per Bank Statement |  |  |  | 150
74 | 13-Mar-2024 | POS Purchase Yoco *Arcata Squa | Food | 22 |  | As Per Bank Statement |  |  |  | 22
75 | 13-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
76 | 13-Mar-2024 | POS Purchase Makro Bloemfontein | Sample Tablets | 2999 | [5 empty] | 2999
78 | 14-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
79 | 15-Mar-2024 | POS Purchase Engen Curie Park Qu | Food | 99.8 |  | As Per Bank Statement |  |  |  | 99.8
80 | 15-Mar-2024 | POS Purchase Bwh Bloemfontein | Petrol | 169 |  | As Per Bank Statement |  |  |  | 169
81 | 15-Mar-2024 | POS Purchase 15.00 Bankstatement | Subscription for Standards use | 287.33 |  | As Per Bank Statement |  |  | 287.33
83 | 16-Mar-2024 | POS Purchase Ae Zastron Str | Food | 61.99 |  | As Per Bank Statement |  |  |  | 61.99
84 | 16-Mar-2024 | POS Purchase Mcd Bloemfontein | Purchase school Licences | 79.8 |  | As Per Bank Statement |  |  |  |  | 79.8
85 | 18-Mar-2024 | FNB App Prepaid Airtime 27631707952 | Airtime | 55 |  | As Per Bank Statement |  |  | 55
86 | 18-Mar-2024 | FNB App Prepaid Airtime 27631707952 | Airtime | 55 |  | As Per Bank Statement |  |  | 55
87 | 19-Mar-2024 | FNB App Prepaid Airtime 27631707952 | Airtime | 55 |  | As Per Bank Statement |  |  | 55
89 | 19-Mar-2024 | Electricity Prepaid Electricity | Airtime | 200 |  | As Per Bank Statement |  |  | 200
90 | 19-Mar-2024 | POS Purchase Chicken Licken Heid | Food | 143 |  | As Per Bank Statement |  |  |  | 143
91 | 19-Mar-2024 | POS Purchase Superspar Aljos | food | 183.49 |  | As Per Bank Statement |  |  |  | 183.49
92 | 20-Mar-2024 | FNB App Prepaid Airtime 27631707952 | Airtime | 55 |  | As Per Bank Statement |  |  | 55
93 | 20-Mar-2024 | POS Purchase Starbucks Fx Mimosa | food | 67 |  | As Per Bank Statement |  |  |  | 67
94 | 20-Mar-2024 | Fuel Purchase Ae Zastron Str | Petrol | 700 |  | As Per Bank Statement |  |  |  |  | 700
95 | 22-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
96 | 22-Mar-2024 | Internet pmt to Makro-Tablets-40 | Procure and deliver of 165 tablets to the selected schools(Purchased 40 out of 165) | 107960 | [5 empty] | 107960
97 | 22-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
98 | 22-Mar-2024 | POS Purchase Ae Zastron Str | food | 38.99 |  | As Per Bank Statement |  |  |  |  | 38.99
99 | 22-Mar-2024 | POS Purchase Sasol Technikon | food | 49.9 |  | As Per Bank Statement |  |  |  |  | 49.9
100 | 22-Mar-2024 | POS Purchase 3.45 Patreon* Membe | Subscription for Standards use | 66.99 |  | As Per Bank Statement |  |  | 66.99
101 | 22-Mar-2024 | Fuel Purchase Shell Botshabelo | Petrol | 300 | [6 empty] | 300
102 | 23-Mar-2024 | Internet Trf To Sisanda Tech | Salary Contracts | 40000 |  |  | 40000
103 | 23-Mar-2024 | FNB App Transfer | Tutor / User Tester | 1200 |  | As Per Bank Statement |  |  |  |  | 1200
104 | 23-Mar-2024 | POS Purchase Belvera Supermarket | Food | 90 |  | As Per Bank Statement |  |  | 90
105 | 25-Mar-2024 | Electricity Prepaid Electricity | Electricity | 200 |  | As Per Bank Statement |  |  | 200
106 | 25-Mar-2024 | POS Purchase Shoprite Botshabelo | Food | 471.33 |  | As Per Bank Statement |  |  | 471.33
107 | 25-Mar-2024 | Fuel Purchase Tshela Filling Stat | Petrol | 150 |  | As Per Bank Statement |  |  |  |  | 150
108 | 25-Mar-2024 | Fuel Purchase Tshela Filling Stat | Petrol | 200 |  | As Per Bank Statement |  |  |  |  | 200
109 | 25-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
110 | 26-Mar-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
111 | 26-Mar-2024 | Fuel Purchase Tshela Filling Stat | Petrol | 150 |  | As Per Bank Statement |  |  |  |  | 150
112 | 26-Mar-2024 | Fuel Purchase Tshela Filling Stat | Petrol | 700 |  | As Per Bank Statement |  |  |  |  | 700
113 | 27-Mar-2024 | FNB App Prepaid Airtime | Airtime | 9 |  | As Per Bank Statement |  |  | 9
115 | 27-Mar-2024 | POS Purchase 52.99 Google *Googl | Subscription for Storage | 52.99 |  | As Per Bank Statement |  |  | 52.99
116 | 02-Apr-2024 | Internet Pmt To 23107Arcatamabaso | Rent | 8500 |  |  |  |  | 8500
117 | 02-Apr-2024 | Internet Pmt To Kajane Sl | Tutor / User Tester | 2350 |  | As Per Bank Statement |  |  |  |  | 2350
118 | 02-Apr-2024 | Internet Pmt To Sgs-Lungile | Tutor / User Tester | 1200 |  | As Per Bank Statement |  |  |  |  | 1200
119 | 02-Apr-2024 | Internet Pmt To Sgs-Neo-Makaye | Tutor / User Tester | 1000 |  | As Per Bank Statement |  |  |  |  | 1000
120 | 02-Apr-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
121 | 02-Apr-2024 | Electricity Prepaid Electricity | Electricity | 200 |  | As Per Bank Statement |  |  | 200
128 | 02-Apr-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
129 | 02-Apr-2024 | Internal Debit Order FNB Insure | FNB Insurance for business | 315 |  | As Per Bank Statement |  |  | 315
130 | 02-Apr-2024 | Magtape Debit Iclix 270026400 Netcash | Subscriptions for standard use(internet) | 450 |  | As Per Bank Statement |  |  | 450
131 | 02-Apr-2024 | POS Purchase Paystack *Xero S | Subscriptions for standard use | 347.5 |  | As Per Bank Statement |  |  | 347.5
132 | 02-Apr-2024 | POS Purchase 109.99 Canva* I0410 | Subscriptions for standard use | 109.99 |  | As Per Bank Statement |  |  | 109.99
133 | 03-Apr-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
134 | 03-Apr-2024 | Magtape Debit Afrihost A16503250 Dmptcvc | Subscriptions for standard use | 229 |  | As Per Bank Statement |  |  | 229
135 | 03-Apr-2024 | Bank Charges March | Bank Charges March | 783.95 |  | As Per Bank Statement |  | 783.95
137 | 04-Apr-2024 | FNB App Prepaid Airtime 27631707952 | Airtime | 55 |  | As Per Bank Statement |  |  | 55
138 | 04-Apr-2024 | FNB App Prepaid Airtime 27631707952 | Airtime | 10 |  | As Per Bank Statement |  |  | 10
139 | 04-Apr-2024 | POS Purchase PNP Crp Bloemgate | Food | 86.18 |  | As Per Bank Statement |  |  |  |  | 86.18
140 | 04-Apr-2024 | POS Purchase Bwh Bloemfontein | Petrol | 334 |  | As Per Bank Statement |  |  |  |  | 334
142 | 05-Apr-2024 | POS Purchase S2S*Willowssupermar | Food | 25 |  | As Per Bank Statement |  |  | 25
143 | 05-Apr-2024 | POS Purchase Belvera Supermarket | Food | 60 |  | As Per Bank Statement |  |  | 60
145 | 06-Apr-2024 | POS Purchase Bwh Bloemfontein | Food | 60 |  | As Per Bank Statement |  |  | 60
146 | 06-Apr-2024 | POS Purchase KFC Bloemfontein | Food | 86.9 |  | As Per Bank Statement |  |  | 86.9
151 | 08-Apr-2024 | POS Purchase Sasol Technikon | Food | 67.8 |  | As Per Bank Statement |  |  | 67.8
152 | 08-Apr-2024 | FNB App Prepaid Airtime | Airtime | 70 |  | As Per Bank Statement |  |  | 70
153 | 09-Apr-2024 | FNB App Transfer | Airtime | 100 |  | As Per Bank Statement |  |  | 100
154 | 09-Apr-2024 | Fuel Purchase Ae Zastron Str | Petrol | 500 |  | As Per Bank Statement |  |  |  |  | 500
155 | 10-Apr-2024 | FNB App Prepaid Airtime | Airtime | 70 |  | As Per Bank Statement |  |  | 70
157 | 11-Apr-2024 | FNB App Prepaid Airtime | Airtime | 70 |  | As Per Bank Statement |  |  | 70
158 | 11-Apr-2024 | FNB App Transfer To Office Equipment Mak | Office equipment | 2400 |  | As Per Bank Statement |  |  | 2400
162 | 11-Apr-2024 | POS Purchase Superspar Aljos | Purchase school Licences | 152.61 |  | As Per Bank Statement |  |  |  |  | 152.61
168 | 13-Apr-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
169 | 15-Apr-2024 | POS Purchase Belvera Supermarket | Food | 68.99 |  | As Per Bank Statement |  |  | 68.99
172 | 15-Apr-2024 | POS Purchase Pf Vuma* Afrihost | Subscriptions for standard use | 529 |  | As Per Bank Statement |  |  | 529
173 | 15-Apr-2024 | FNB App Transfer To Lunch | Food | 60 |  | As Per Bank Statement |  |  | 60
174 | 16-Apr-2024 | POS Purchase Starbucks Fx Mimosa | Food | 12 |  | As Per Bank Statement |  |  | 12
175 | 16-Apr-2024 | POS Purchase Tshela Filling Stat | Food | 39 |  | As Per Bank Statement |  |  | 39
176 | 16-Apr-2024 | POS Purchase 15.00 Bankstatement | Subscriptions for standard use | 290.5 |  | As Per Bank Statement |  |  | 290.5
177 | 16-Apr-2024 | Fuel Purchase Shell Gysie Pienaar | Petrol | 500.15 |  | As Per Bank Statement |  |  |  |  | 500.15
178 | 16-Apr-2024 | Fuel Purchase Tshela Filling Stat | Petrol | 700 |  | As Per Bank Statement |  |  |  |  | 700
180 | 17-Apr-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
182 | 17-Apr-2024 | Electricity Prepaid Electricity | Electricity | 200 |  | As Per Bank Statement |  |  | 200
183 | 17-Apr-2024 | FNB App Prepaid Airtime | Airtime | 55 |  | As Per Bank Statement |  |  | 55
184 | 17-Apr-2024 | POS Purchase 52.99 Google *Googl | Subscription for standard use | 52.99 |  | As Per Bank Statement |  |  | 52.99
185 | 17-Apr-2024 | Send Money App Dr | Tutor / User Tester | 500 |  | As Per Bank Statement |  |  |  |  | 500
187 | 22-Apr-2024 | POS Purchase 3.45 Patreon* Membe | Subscription for Standard use | 67.63 |  | As Per Bank Statement |  |  | 67.63
188 | 22-Apr-2024 | Fuel Purchase Engen Mangaung 1 St | Petrol | 500 |  | As Per Bank Statement |  |  |  |  | 500
189 | 23-Apr-2024 | Internet Pmt To Sarseflng 0082478171 | Sars Filling | 800 |  | As Per Bank Statement |  | 800
190 | 23-Apr-2024 | Internet Pmt To Sarseflng 0082478385 | Sars Filling | 420 |  | As Per Bank Statement |  | 420
191 | 23-Apr-2024 | Electricity Prepaid Electricity | Electricity | 200 |  | As Per Bank Statement |  |  | 200
192 | 26-Apr-2024 | POS Purchase Cash Crusaders | Office equipment | 549 |  | As Per Bank Statement |  |  | 549
193 | 29-Apr-2024 | POS Purchase Emma Booysen Photog | Photography | 700 |  | As Per Bank Statement |  |  | 700
194 | 29-Apr-2024 | POS Purchase 109.99 Google *Yout | Subscription for Standard Use | 109.99 |  | As Per Bank Statement |  |  |  |  | 109.99
195 | 29-Apr-2024 | Fuel Purchase Ae Zastron Str | Petrol | 700 |  | As Per Bank Statement |  |  |  | 700
196 | 30-Apr-2024 | Electricity Prepaid Electricity | Electricity | 200 |  | As Per Bank Statement |  |  | 200
197 | 30-Apr-2024 | Internet Trf To Basosalary | Salary Contracts | 13000 |  | As Per Bank Statement | 13000
198 | 30-Apr-2024 | Send Money App Dr Send | Tutor / User Tester | 1300 |  | As Per Bank Statement |  |  |  |  | 1300
199 | 30-Apr-2024 | FNB App Prepaid Airtime | Airtime | 70 |  | As Per Bank Statement |  |  | 70
200 | 30-Apr-2024 | Magtape Debit Iclix | Subscription for Standards use | 450 |  |  |  |  | 450
201 | 02-May-2024 | Send Money App | Tutor / User Tester | 1300 |  | As Per Bank Statement |  |  |  | 1300
202 | 02-May-2024 | Internal Debit Order FNB Insure | FNB Insurance for business | 315 |  | As Per Bank Statement |  |  | 315
203 | 02-May-2024 | Magtape Debit Afrihost | Subscription for Standards use | 225 |  |  |  |  | 225
205 | 02-May-2024 | POS Purchase Paystack *Xero S | Subscription for Standards use | 347.5 |  |  |  |  | 347.5
206 | 02-May-2024 | POS Purchase 109.99 Canva* I0413 | Subscription for Standards use | 109.99 |  |  |  |  | 109.99
208 | 04-May-2024 | POS Purchase Pf Vuma* Afrihost | Subscription for Standards use | 191.3 |  |  |  |  | 191.3
209 | 06-May-2024 | POS Purchase Superspar Aljos | Food | 120.34 |  | As Per Bank Statement |  |  | 120.34
210 | 06-May-2024 | POS Purchase 34.50 Cgtrader | Digital assets for project | 658.28 |  | As Per Bank Statement |  |  |  | 658.28
211 | 07-May-2024 | Internet Pmt To Sgs-Neo-Makaye | Tutor / User Tester | 500 |  | As Per Bank Statement |  |  |  | 500
213 | 11-May-2024 | POS Purchase 25.00 Unity | Digital assets for project | 476.45 |  | As Per Bank Statement |  |  |  | 476.45
214 | 14-May-2024 | Electricity Prepaid Electricity | Electricity | 200 |  | As Per Bank Statement |  |  | 200
217 | 16-May-2024 | Card Purchase With Cashback Superspar Aljos | Food | 32.4 |  | As Per Bank Statement |  |  | 32.4
218 | 16-May-2024 | Card Cashback Cashb Superspar Aljo | Food | 200 |  | As Per Bank Statement |  |  | 200
219 | 16-May-2024 | POS Purchase Sps B | Airtime | 663 |  | As Per Bank Statement |  |  | 663
220 | 18-May-2024 | POS Purchase Yoco *Arcata Squa | Food | 22 |  | As Per Bank Statement |  |  | 22
221 | 18-May-2024 | POS Purchase 15.00 Bankstatement | Subscriptions for standard use | 280.35 |  |  |  |  | 280.35
TOTAL |  |  |  | 283825.39 |  |  | 74000 | 2717.69 | 30887.87 | 136039 | 40180.83

## Quarterly financial
DETAILED EXPENSE REPORT - QUARTERLY
Name of Institution:
Current Reporting Period: |  |  |  | Jan - March 2024
Agreement Period:
Agreement No:
Invoice Number:
(Information in the budget section must be aligned with agreed budget according to the project plan and contract. Please ensure the budget is sufficiently detailed and add notes to explain all significant variations from budget.
| Budget for Quarter | Actual for Quarter | Variance | % Variance | Reasons for variances | Comments
INCOME |  |  | (For all income= Actual for the quarter less budget for the quarter) | (% variance= variance/actual for the quarter) | (All reasons for variances can be detailed on the page below; you can also include any further notes) | For any expenditure over R100k, please provide details in the form of notes linked to the project activity
Balance brought forward from previous quarter (this should be the surplus/ (deficit) from previous quarter) | 0
TIA Funding received/budgeted in the quarter | 924000 | 283825.39 | 640174.61 | 69.28% | Budget is more than the funds tranfered by TIA | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing
Other Income: | 0 | 0 | 0 | 0%
Interest | 0 | 0 | 0 | 0%
VAT refund | 0 | 0 | 0 | 0%
etc. | 0 | 0 | 0 | 0%
GRAND TOTAL INCOME | 924000 | 283825.39 | 640174.61 | 69.28% | Budget is more than the funds tranfered by TIA | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing
EXPENSES (allocated to TIA funding) | 924000 | 283825.39 | 640174.61 | (% variance= variance/budget for the quarter) | Budget is more than the funds tranfered by TIA | (For all expenses= Budget for the quarter less actual for the quarter)
PERSONNEL COSTS: | 15000 | 74000 | -59000 | -79.73%
1.1.1 Understand project objectives, scope, and deliverables [Mbangiso Mabaso] | 0 | 0 | 0 | 0%
1.1.2 Ensure all project related contracts are in place for the project [Mbangiso Mabaso] | 0 | 0 | 0 | 0%
2.2.1 Develop Project Execution Plan in consultation with TIA Specialist[Mbangiso Mabaso + Ashaal] | 0 | 0 | 0 | 0%
2.2.2 Host Project kick off meeting to ensure all relevant stakeholders understand how the project will be implemented[Mbangiso Mabaso + TIA +DSI+City of Umhlathuze) | 0 | 0 | 0 | 0%
2.2.3 Develop a stakholder map to identifiy funding sources and potential partners for Umhlatuze | 0 | 0 | 0 | 0%
2.2.4 Develop a business sustainability model for Sisanda App Universe | 0 | 0 | 0 | 0%
2.2.5 Source funding proposals to support the sustainability of Sisanda App Universe beyond the duration of this project at Umhlathuze | 0 | 0 | 0 | 0%
3.1.1 Identify and finalise product sites[Mbangiso Mabaso] | 0 | 0 | 0 | 0%
3.1.2 Address any potential gaps that might impact project implementation[Mbangiso Mabaso] | 0 | 0 | 0 | 0%
3.1.5 Install the app on tablets for all participating schools[Mbangiso Mabaso/Lepekoloa Lenkoe] | 5000 | 21000 | -16000 | -76.19% | Had more meetings than expected and I had to travel several times and also but food for training team | https://drive.google.com/file/d/17ZrGKJxsQAJ4TKUtzxKRohzbZU8BRphe/view?usp=drive_link
3.1.6 Conduct quality assurance checks to ensure optimal app performance of the app on all devices[Mbangiso Mabaso/Lepekoloa Lenkoe] | 0 | 0 | 0 | 0%
4.2.3 Schedule training sessions for teachers and IT staff.[Mbangiso Mabaso] | 0 | 0 | 0 | 0%
3.2.1 Conduct hands-on demonstration sessions. | 5000 | 40000 | -35000 | -87.5% | Drafting of contracts to be given to each recipient of the tablet and also with the schools | https://drive.google.com/file/d/1rHCW3M-RDxL2_y-eoMklQJXRwQye6Tb3/view?usp=drive_link
3.2.3 Update and distribute user manuals and FAQs. | 0 | 0 | 0 | 0%
3.3.1 Distribute tablets to the schools [Mbangiso Mabaso + Vuyisile Mdutjulwa] | 0 | 0 | 0 | 0%
3.3.2 Provide delivery notes for teachers or school management to sign, confirming delivery. | 5000 | 13000 | -8000 | -61.54% | We under budgetted for this one as it costed us more than what we planned | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing
3.3.3 Provide on-site support during the initial days of implementation. | 0 | 0 | 0 | 0%
4.1.1 Establish a helpline or support portal for schools to report issues or seek assistance. | 0 | 0 | 0 | 0%
4.1.2 Monitor app usage, performance, and gather user feedback. | 0 | 0 | 0 | 0%
4.1.3 Provide any and all required updates to the Sisanda App. | 0 | 0 | 0 | 0%
4.3.1 Release updates or patches based on feedback and technological advancements. | 0 | 0 | 0 | 0%
4.3.2 Schedule refresher training sessions on any new features added to the app | 0 | 0 | 0 | 0%
4.3.3 Engage with schools for sustained collaboration and improvement. | 0 | 0 | 0 | 0%
OPERATIONAL COST: | 0 | 2717.69 | -2717.69 | -100%
Overheads/Admin/ Bank Charge | 0 | 2717.69 | -2717.69 | -100% | This was not part of the budget especially bank charges | As per bank statement
CAPITAL EQUIPMENT: | 909000 | 207107.7 | 701892.3
Procure and deliver of 165 tablets to the selected schools(Purchased 40 out of 165) | 506664 | 166926.87 | 339737.13 | 67.05% | All Tablets will be bought in Q2. We are currently settling the matter of cloud storage and other subcriptions | As per bank statement
Purchase school Licences | 402336 | 40180.83 | 362155.17 | 90.01% | This Activity will be fully achieved in Q2 | As per bank statement
CONSUMABLES: | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
GRAND TOTAL EXPENDITURE: : | 924000 | 283825.39 | 640174.61 | 69.28%
SURPLUS/(DEFICIT) |  | 640174.61
(Grand Total Income less Grand Total Expenditure)
Declaration: I hereby declare that the information supplied is a true reflection of the financial records of Project (Insert Project name and number)
Financial information prepared by: Yasmin
Signature:
Date: 13 June 2024
Financial Information Approved By: Nondumiso
Signature:
Date: 13 June 2024

## Next Quarter Projection
Quarter Projection
Name of Institution: | ABC Academy
Current Reporting Period: | Q1
Projection Period: | Q2
INCOME | Budget for Quarter
Balance brought forward from previous quarter (this should be the surplus/ (deficit) from previous quarter) | 640174.61
TIA Funding received/budgeted in the quarter | 25000
Total Budget | 665174.61
PROJECTED EXPENDITURE | 741892.3 | Activity Details ( Include details of activitives linked to the budget line item in the approved project plan)
PERSONNEL COSTS: | 30000
Develop a stakholder map to identifiy funding sources and potential partners for Umhlatuze | 20000
Develop a business sustainability model for Sisanda App Universe
Source funding proposals to support the sustainability of Sisanda App Universe beyond the duration of this project at Umhlathuze
Schdeule training sessions for teachers and IT staff. | 5000
Conduct hands-on demonstration sessions.
Update and distribute user manuals and FAQs.
Distribute tablets to the schools. | 5000
Provide delivery notes for teachers or school management to sign, confirming delivery.
Provide on-site support during the initial days of implementation.
OPERATIONAL COST: | 10000
Establish a helpline or support portal for schools to report issues or seek assistance. | 5000
Monitor app usage, performance, and gather user feedback.
Provide any and all required updates to the Sisanda App.
Release updates or patches based on feedback and technological advancements. | 5000
Schedule refresher training sessions on any new features added to the app
Engage with schools for sustained collaboration and improvement.
CAPITAL EQUIPMENT: | 701892.3
Procure and deliver of 165 tablets to the selected schools | 339737.13 | This amount is carried over from the remaining funds in Q1
Purchase school Licences | 362155.17 | This amount is carried over from the remaining funds in Q2
Sub-contracting/ consultants | 0
0
CONSUMABLES: | 0
0
0
0
0
GRAND TOTAL PROJECTION: : | 741892.3
SURPLUS / DEFICIT | -76717.69 | (Provide notes for anticipated surplus or deficit)
Declaration: I hereby declare that the information supplied is a true reflection of the financial records of Project (Insert Project name and number)
Financial information prepared by: Yasmin
Signature:
Date: 13 June 2024
Financial Information Approved By: Nondumiso
Signature:
Date: 13 June 2024

## Bank and cash reconciliation
BANK AND CASH RECONCILIATION
Name of Institution: ABC Academy
Current Reporting Period: Jan - March 2024
Agreement Period: Q1
Agreement No:
Invoice Number:
| R | R
Amount Transferred from TIA |  | 300000
Less Actual Expenses |  | 268326.39
Surplus (deficit) |  | 31673.61
(from above)
Reconciling items:
Bank and cash balance |  | 31673.61
(as in bank statement balances for all bank accounts held, physical cash holdings, or as in university or council cost centre statement, where applicable)

## Accumulated financial info
| Project Budget to date | Project Actual to date | Variance | % Variance
INCOME |  |  | (For all income= Actual year to date less budget year to date) | (% variance= variance/actual year to date)
TIA Funding | 924000 | 283825.39 | -640174.61 | -69.28%
Co- funding received : | 0 | 0 | 0
Consortium Partner A | 0 | 0 | 0
Consortium Partner B | 0 | 0 | 0
Consortium Partner C | 0 | 0 | 0
Consortium Partner D | 0 | 0 | 0
Other income: | 0 | 0 | 0
Interest | 0 | 0 | 0
VAT refund | 0 | 0 | 0
etc. | 0 | 0 | 0
Grand Total Income | 924000 | 283825.39 | -640174.61 | -69.28%
EXPENSES (allocated to TIA funding) | 924000 | 283825.39 | (For all expenses= Budget year to date less actual year to date) | (% variance= variance/budget year to date)
Personnel costs: | 15000 | 74000 | -59000 | -79.73%
(Project related human resources salaries, bonuses etc.) | 0 | 0 | 0 | 0%
1.1.1 Understand project objectives, scope, and deliverables [Mbangiso Mabaso] | 0 | 0 | 0 | 0%
1.1.2 Ensure all project related contracts are in place for the project [Mbangiso Mabaso] | 0 | 0 | 0 | 0%
2.2.1 Develop Project Execution Plan in consultation with TIA Specialist[Mbangiso Mabaso + Ashaal] | 0 | 0 | 0 | 0%
2.2.2 Host Project kick off meeting to ensure all relevant stakeholders understand how the project will be implemented[Mbangiso Mabaso + TIA +DSI+City of Umhlathuze) | 0 | 0 | 0 | 0%
2.2.3 Develop a stakholder map to identifiy funding sources and potential partners for Umhlatuze | 0 | 0 | 0 | 0%
2.2.4 Develop a business sustainability model for Sisanda App Universe | 0 | 0 | 0 | 0%
2.2.5 Source funding proposals to support the sustainability of Sisanda App Universe beyond the duration of this project at Umhlathuze | 0 | 0 | 0 | 0%
3.1.1 Identify and finalise product sites[Mbangiso Mabaso] | 0 | 0 | 0 | 0%
3.1.2 Address any potential gaps that might impact project implementation[Mbangiso Mabaso] | 0 | 0 | 0 | 0%
3.1.5 Install the app on tablets for all participating schools[Mbangiso Mabaso/Lepekoloa Lenkoe] | 5000 | 21000 | -16000 | -76.19%
3.1.6 Conduct quality assurance checks to ensure optimal app performance of the app on all devices[Mbangiso Mabaso/Lepekoloa Lenkoe] | 0 | 0 | 0 | 0%
4.2.3 Schedule training sessions for teachers and IT staff.[Mbangiso Mabaso] | 0 | 0 | 0 | 0%
3.2.1 Conduct hands-on demonstration sessions. | 5000 | 40000 | -35000 | -87.5%
3.2.3 Update and distribute user manuals and FAQs. | 0 | 0 | 0 | 0%
3.3.1 Distribute tablets to the schools [Mbangiso Mabaso + Vuyisile Mdutjulwa] | 0 | 0 | 0 | 0%
3.3.2 Provide delivery notes for teachers or school management to sign, confirming delivery. | 5000 | 13000 | -8000 | -61.54%
3.3.3 Provide on-site support during the initial days of implementation. | 0 | 0 | 0 | 0%
4.3.3 Engage with schools for sustained collaboration and improvement. | 0 | 0 | 0 | 0%
Operational costs: | 0 | 2717.69 | -2717.69 | -100%
(E.g. equipment maintenance, travel etc.) | 0 | 0 | 0 | 0%
Overheads/Admin/ Bank Charge | 0 | 2717.69 | -2717.69 | 0%
Capital equipment: | 909000 | 207107.7 | 701892.3 | 77.22%
(put detailed capital items purchased individually or in groups as applicable) | 0 | 0 | 0 | 0%
Procure and deliver of 165 tablets to the selected schools(Purchased 40 out of 165) | 506664 | 166926.87 | 339737.13 | 67.05%
Purchase school Licences | 402336 | 40180.83 | 362155.17 | 90.01%
Sub-contracting/ consultants | 0 | 0 | 0 | 0%
(all consultants used should be disclosed individually) | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
Consumables: | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
Contingency: | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
Total expenses allocated to TIA funding: | 924000 | 283825.39 | 642892.3 | 69.58%
Co- funding total expenses:
(Insert totals of project expenses by each consortium partner; supporting documents for these totals must be readily available for TIA when requested.)
Consortium Partner A | 0 | 0 | 0 | 0%
Consortium Partner B | 0 | 0 | 0 | 0%
Consortium Partner C | 0 | 0 | 0 | 0%
Consortium Partner D | 0 | 0 | 0 | 0%
Grand Total Expenditure: | 924000 | 283825.39 | 642892.3 | 69.58%
SURPLUS/(DEFICIT) |  | 640174.61
(Grand Total Income less Grand Total Expenditure)
(This amount above should be the same as the surplus / (deficit) for the current quarter)