## Project Plan
Milestone | Work Package | Objective | Activities |  | Deliverables | Format of Deliverable | Timeframe |  |  | Year 1 Budget incl. VAT |  |  |  | TOTAL
|  |  | No. | Details |  |  | Start (Month) | End (Month) | Duration | Quarter 1 | Quarter 2 | Quarter 3 | Quarter 4
1. Initiation | 1.1. Project Legal & Administration | To ensure project management and legal & administration requirements are in place for the successful implementation of the project | 1.1.1 | Understand project objectives, scope, and deliverables. | Completed project proposal | PDF | Month 1 | Month 1 | 1 Month | 0 | 0 | 0 | 0
|  |  | 1.1.2 | Ensure all project related contracts are in place for the project | Signed Contracts
Sub-Total 1 | [10 empty] | 0 | 0 | 0 | 0
2. Planning | 2.1 Project Planning | Establish a clear, legally binding framework for the project, ensuring collaboration and understanding between all parties. | 2.2.1 | Develop Project Execution Plan in consultation with TIA Specialits | Project Execution Document | PDF | Month 1 | Month 1 | 1 Month | 0 | 0 | 0 | 0
|  |  | 2.2.2 | Host Project kick off meeting to ensure all relevant stakholders understand how the project will be implemented
| 2.2. Business Sustainability Model | To build a business sustainability model that aims to reduce dependence on government support for the technology in the future. | 2.2.3 | Develop a stakholder map to identifiy funding sources and potential partners for Umhlatuze | Stakeholder map including funding sources |  | Month 1 | Month 2 | 12 Months | 0 | 20000 | 20000 | 10000
|  |  | 2.2.4 | Develop a business sustainability model for Sisanda App Universe | Business sustainability model |  | Month 3 | Month 9
|  |  | 2.2.5 | Source funding proposals to support the sustainability of Sisanda App Universe beyond the duration of this project at Umhlathuze | 3 Funding Proposals |  | Month 9 | Month 12
Sub-Total 2 | [10 empty] | 20000 | 20000 | 10000 | 50000
3. Execution (Deployment) | 3.1. Deployment Readiness | To prepare for deployment of the Sisanda App at all selcted schools | 3.1.1 | Identify and finalize product sites | Finalized list of sites signed off by City of uMhlathuze | PDF | Month 2 | Month 2 | 1 Week | 0 |  | 0 | 0
|  |  | 3.1.2 | Address any potential gaps that might impact project implementation. | Updated Risk Register | Excel Sheet | Month 2 | Month 2 | 2 Week | 0 |  | 0 | 0 | 0
|  |  | 3.1.3 | Procure and deliver of 165 tablets to the selected schools | Invoice and Delivery Notes. | PDF | Month 2 | Month 2 | 1 Week | 506664 |  |  |  | 506664
|  |  | 3.1.4 | Purchase school Licences | Proof of payment of licenses | .xsl | Month 2 | Month 2 | 1 Week | 402336 |  | 0 | 0 | 402336
|  |  | 3.1.5 | Install the app on tablets for all participating schools. | Successful installation test report for all devices | .apk | Month 2 | Month 2 | 1 Week | 0 |  | 0 | 0 | 0
|  |  | 3.1.6 | Conduct quality assurance checks to ensure optimal app performance of the app on all devices | Quality Assurance Report | PDF | Month 2 | Month 2 | 1 Week
| 3..2 Training | To Equip teachers and IT staff with the skills to use the app effectively. | 3.2..1 | Schdeule training sessions for teachers and IT staff. | Scanned Attendance Register and Training Report | PDF | Month 3 | Month 3 | 1 Month | 5000 | 0 | 0 | 0
|  |  | 3.2..2 | Conduct hands-on demonstration sessions. | Scanned Attendance Register and Training Report | Website Page
|  |  | 3.2..3 | Update and distribute user manuals and FAQs. | Proof of updated manuals and distribution lsists | Printed Manuals
| 3.3 Deployment | To successfully roll out the app across the selected designated schools. | 3.3.1 | Distribute tablets to the schools. | Signed delivery notes | PDF | Month 3 | Month 12 | 8 Month | 5000 | 0 | 0 | 0
|  |  | 3.3.2 | Provide delivery notes for teachers or school management to sign, confirming delivery.
|  |  | 3.3.3 | Provide on-site support during the initial days of implementation.
Sub-Total 3 | [10 empty] | 0 | 0 | 0
4. Support, Monitoring and Evaluation | 4.1.Monitoring and Support | To ensure smooth app operation and address any arising issues. | 4.1.1 | Establish a helpline or support portal for schools to report issues or seek assistance. | Support portal | Online Portal | Month 3 | Month 12 | 9 Month | 5000 | 0 | 6000 | 0
|  |  | 4.1.2 | Monitor app usage, performance, and gather user feedback. | Monthly monitoring reports | PDF
|  |  | 4.1.3 | Provide any and all required updates to the Sisanda App. | Update Reports | APK
| 4.2. Feedback Collection | To assess user experience and identify areas for improvement. | 4.2.1 | Conduct surveys or focus group discussions with teachers and students. | Feedback reports from users | PDF | Month 3 | Month 12 | 9 Month | 0 | 0 | 0 | 0
|  |  | 4.2.2 | Analyze feedback to discern trends, challenges, or suggestions. | Feedback reports from users | PDF
|  |  | 4.2.3 | Plan enhancements based on the feedback received. | Update Product roadmap | Trello
| 4.3.Continuous Improvement | To ensure the app's continued relevance and efficacy. | 4.3.1 | Release updates or patches based on feedback and technological advancements. | Updated app versions | APK | Month 3 | Month 12 | 9 Month | 0 | 5000 | 5000 | 5000
|  |  | 4.3.2 | Schedule refresher training sessions on any new features added to the app | Training sessions for new features | PDF and Support page
|  |  | 4.3.3 | Engage with schools for sustained collaboration and improvement. | Feedback reports | PDF
Sub-Total 4 | [10 empty] | 5000 | 11000 | 5000 | 26000
5. Closure | 5.1.Project Review and Reporting | Conclude the implementation phase and transition to regular operations. | 5.1.1 | Document the implementation process, challenges encountered, and lessons learned. | Final project close out eport | PDF | Month 10 | Month 12 | 2 Month | 0 | 0 | 0 | 5000
Sub-Total 5 | [10 empty] | 0 | 0 | 5000 | 5000
Grand Total (Sub-Total 1 +2+3+4+5) | [10 empty] | 25000 | 31000 | 20000 | 1000000
Disbursement Schedule
| Disbursement 1 (30%) | 300000
Disbursement 2 (50%)
| Disbursement 3 (20%) | 200000

## Breakdown expediture
Sisanda.com
| INVOICES | [5 empty] | LABOUR | OPERATIONAL COST: |  | CAPITAL EQUIPMENT
nr | Date | Name of Company | Description | Invoice | Link for invoice | Link for POP | Personnel | Overheads/Admin/ Bank Charge | Office material and Rent | Procure and deliver of 165 tablets to the selected schools | Purchase school Licences
TOTAL

## Quarterly financial
DETAILED EXPENSE REPORT - QUARTERLY
Name of Institution:
Current Reporting Period: |  |  |  | Jan - March 2024
Agreement Period:
Agreement No:
Invoice Number:
(Information in the budget section must be aligned with agreed budget according to the project plan and contract. Please ensure the budget is sufficiently detailed and add notes to explain all significant variations from budget.
| Budget for Quarter | Actual for Quarter | Variance | % Variance | Reasons for variances | Comments
INCOME |  |  | (For all income= Actual for the quarter less budget for the quarter) | (% variance= variance/actual for the quarter) | (All reasons for variances can be detailed on the page below; you can also include any further notes) | For any expenditure over R100k, please provide details in the form of notes linked to the project activity
Balance brought forward from previous quarter (this should be the surplus/ (deficit) from previous quarter) | 0
TIA Funding received/budgeted in the quarter | 924000 |  |  |  | Budget is more than the funds tranfered by TIA | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing
Other Income: | 0 | 0 |  | 0%
Interest | 0 | 0 | 0 | 0%
VAT refund | 0 | 0 | 0 | 0%
etc. | 0 | 0 | 0 | 0%
GRAND TOTAL INCOME |  |  |  |  | Budget is more than the funds tranfered by TIA | https://drive.google.com/file/d/1qVQtyr7AXdiVotWmxgNo4LdfyX6nrc14/view?usp=sharing
EXPENSES (allocated to TIA funding) |  |  |  | (% variance= variance/budget for the quarter) | Budget is more than the funds tranfered by TIA | (For all expenses= Budget for the quarter less actual for the quarter)
PERSONNEL COSTS:
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
OPERATIONAL COST:
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
CAPITAL EQUIPMENT:
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
CONSUMABLES: |  |  |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
| 0 | 0 |  | 0%
GRAND TOTAL EXPENDITURE: :
SURPLUS/(DEFICIT)
(Grand Total Income less Grand Total Expenditure)
Declaration: I hereby declare that the information supplied is a true reflection of the financial records of Project (Insert Project name and number)
Financial information prepared by: Yasmin
Signature:
Date: 13 June 2024
Financial Information Approved By: Nondumiso
Signature:
Date: 13 June 2024

## Next Quarter Projection
Quarter Projection
Name of Institution: | ABC Academy
Current Reporting Period: | Q1
Projection Period: | Q2
INCOME | Budget for Quarter
Balance brought forward from previous quarter (this should be the surplus/ (deficit) from previous quarter)
TIA Funding received/budgeted in the quarter | 25000
Total Budget
PROJECTED EXPENDITURE |  | Activity Details ( Include details of activitives linked to the budget line item in the approved project plan)
PERSONNEL COSTS:
Develop a stakholder map to identifiy funding sources and potential partners for Umhlatuze | 20000
Develop a business sustainability model for Sisanda App Universe
Source funding proposals to support the sustainability of Sisanda App Universe beyond the duration of this project at Umhlathuze
Schdeule training sessions for teachers and IT staff. | 5000
Conduct hands-on demonstration sessions.
Update and distribute user manuals and FAQs.
Distribute tablets to the schools. | 5000
Provide delivery notes for teachers or school management to sign, confirming delivery.
Provide on-site support during the initial days of implementation.
OPERATIONAL COST:
Establish a helpline or support portal for schools to report issues or seek assistance. | 5000
Monitor app usage, performance, and gather user feedback.
Provide any and all required updates to the Sisanda App.
Release updates or patches based on feedback and technological advancements. | 5000
Schedule refresher training sessions on any new features added to the app
Engage with schools for sustained collaboration and improvement.
CAPITAL EQUIPMENT:
Procure and deliver of 165 tablets to the selected schools |  | This amount is carried over from the remaining funds in Q1
Purchase school Licences |  | This amount is carried over from the remaining funds in Q2
Sub-contracting/ consultants
0
CONSUMABLES:
0
0
0
0
GRAND TOTAL PROJECTION: :
SURPLUS / DEFICIT |  | (Provide notes for anticipated surplus or deficit)
Declaration: I hereby declare that the information supplied is a true reflection of the financial records of Project (Insert Project name and number)
Financial information prepared by: Yasmin
Signature:
Date: 13 June 2024
Financial Information Approved By: Nondumiso
Signature:
Date: 13 June 2024

## Bank and cash reconciliation
BANK AND CASH RECONCILIATION
Name of Institution: ABC Academy
Current Reporting Period: Jan - March 2024
Agreement Period: Q1
Agreement No:
Invoice Number:
| R | R
Amount Transferred from TIA |  | 300000
Less Actual Expenses
Surplus (deficit)
(from above)
Reconciling items:
Bank and cash balance
(as in bank statement balances for all bank accounts held, physical cash holdings, or as in university or council cost centre statement, where applicable)

## Accumulated financial info
| Project Budget to date | Project Actual to date | Variance | % Variance
INCOME |  |  | (For all income= Actual year to date less budget year to date) | (% variance= variance/actual year to date)
TIA Funding
Co- funding received : | 0 | 0 | 0
Consortium Partner A | 0 | 0 | 0
Consortium Partner B | 0 | 0 | 0
Consortium Partner C | 0 | 0 | 0
Consortium Partner D | 0 | 0 | 0
Other income: | 0 | 0 | 0
Interest | 0 | 0 | 0
VAT refund | 0 | 0 | 0
etc. | 0 | 0 | 0
Grand Total Income |  |  | -640174.61
EXPENSES (allocated to TIA funding) |  |  | (For all expenses= Budget year to date less actual year to date) | (% variance= variance/budget year to date)
Personnel costs:
(Project related human resources salaries, bonuses etc.) | 0 | 0 | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
|  |  | 0 | 0%
Operational costs:
(E.g. equipment maintenance, travel etc.) | 0 | 0 | 0 | 0%
Overheads/Admin/ Bank Charge | 0 |  | -2717.69 | 0%
Capital equipment:
(put detailed capital items purchased individually or in groups as applicable) | 0 | 0 | 0 | 0%
|  |  | 339737.13 | 67.05%
|  |  | 362155.17 | 90.01%
Sub-contracting/ consultants |  |  |  | 0%
(all consultants used should be disclosed individually) | 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
Consumables: | 0 | 0 |  | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
Contingency: |  |  |  | 0%
| 0 | 0 | 0 | 0%
| 0 | 0 | 0 | 0%
Total expenses allocated to TIA funding:
Co- funding total expenses:
(Insert totals of project expenses by each consortium partner; supporting documents for these totals must be readily available for TIA when requested.)
Consortium Partner A | 0 | 0 |  | 0%
Consortium Partner B | 0 | 0 | 0 | 0%
Consortium Partner C | 0 | 0 | 0 | 0%
Consortium Partner D | 0 | 0 | 0 | 0%
Grand Total Expenditure: |  | 283825.39 | 642892.3
SURPLUS/(DEFICIT)
(Grand Total Income less Grand Total Expenditure)
(This amount above should be the same as the surplus / (deficit) for the current quarter)